Table of Contents

# Handwritten-Digit NPU on a Basys3 (Artix-7 XC7A35T) — Research + Build Roadmap

Target: a custom NPU in RTL on the Basys3, classifying hand-drawn digits that the user draws at ~50x50, with the model trained locally (PyTorch) and quantized to fixed-point for the fabric.

## 0. Verdict

Feasible. Not "feasible with heroics" — comfortably feasible, and the textbook third-project for someone with your background (Verilog, cocotb, Vivado, RISC-V soft core already working on this board).

The three things that actually gate this project, in order:

- Engineering time (the real cost — a CNN engine is ~2–4 months of part-time work for a first build).

- Input transport (UART), not compute. A 50x50 frame = 2500 bytes; at 115200 baud that is 217 ms/frame → ~5 inferences/s end-to-end. Compute is ~100 us. Your accelerator will be idle 99.8% of the time at default baud. Fix by raising baud (FT2232H bridge does 1–3 Mbaud easily) or by streaming a stored test set.

- Weight storage in BRAM (225 KiB total, 50 x 36Kb blocks) — this is what forces your quantisation and architecture decisions, and it is the one hard number to design around.

Compute is not a problem: 90 DSP48E1 (25x18 multiplier + 48-bit accumulator + pre-adder) at 100 MHz gives you 9 GMAC/s if you use all 90. MNIST-class models need ~0.05–1 MMAC per inference.

## 1. Hardware envelope (verified)

| Resource | XC7A35T-1CPG236C (Basys3) |
| --- | --- |
| Slices / LUT6 / FF | 5,200 / 20,800 / 41,600 (Digilent: "33,280 logic cells") |
| DSP slices | 90 x DSP48E1 (25x18 signed mult, 48-bit accumulate, pre-adder) |
| Block RAM | 1,800 Kb = 225 KiB = 50 x 36Kb RAMB36E1 (byte-wide mode: 4 KiB usable per block) |
| Clocking | 5 CMT (PLL/MMCM); board oscillator 100 MHz on pin W5 |
| External memory | none (no DDR) — weights must live in BRAM/LUT ROM |
| Storage | 32 Mbit (4 MB) QSPI flash (configuration + spare space for a small dataset) |
| Host I/O | USB-UART bridge FT2232H (up to 12 Mbaud; 115200 default) |
| Display | 4-digit 7-seg, 16 LEDs, 16 switches, 5 buttons, 12-bit VGA |
| Expansion | 3 Pmod + 1 XADC Pmod |

Upgrade path if you outgrow it: Arty A7-100T (XC7A100T: 15,850 slices / 4,860 Kb BRAM / 240 DSP) — same RTL, same flow, 2.7x BRAM. Pynq-Z2/Zybo adds an ARM + DDR, which is what the finished toolchains (FINN, Vitis AI DPU) actually require.

## 2. The arithmetic of your specific problem

50x50 input is the risky part, and it is not the compute — it is the first layer's weights.

A fully-connected first layer on 2,500 inputs blows the BRAM budget at int8:

| Model | Params | Weights @8-bit | BRAM blocks | Verdict |
| --- | --- | --- | --- | --- |
| MLP 2500-128-64-10 | 329,034 | 321 KiB | 80 / 50 | does not fit |
| MLP 2500-128-64-10 @4-bit | 329,034 | 161 KiB | 40 / 50 | fits, tight |
| MLP 2500-128-64-10 @1-bit (BNN) | 329,034 | 40 KiB | 10 / 50 | fits easily |
| MLP 784-64-32-10 @8-bit (28x28) | 52,650 | 51 KiB | 13 / 50 | fits easily |
| CNN 50x50 (3x3 1→8, pool, 3x3 8→16, pool, FC→10) | 20,618 | 20 KiB | 5 / 50 | fits with room to spare |

The same CNN needs 862,912 MACs/inference — 26,966 cycles at 32 MACs/cycle (~270 us at 100 MHz, ~3,700 inf/s). So the conv front-end costs you compute you have in abundance and saves you the memory you don't. Conclusion: do not build a 2500-input MLP. Build a small CNN, or use ≤4-bit weights.

Latency vs parallelism (100 MHz), for planning:

| Model | MACs | P=8 | P=32 | P=64 | P=81 |
| --- | --- | --- | --- | --- | --- |
| MLP 784-64-32-10 @8b | 52,544 | 66 us | 16 us | 8 us | 6.5 us |
| CNN 50x50 @8b | 862,912 | 1,079 us | 270 us | 135 us | 107 us |

Even an 8-MAC design (8 DSPs, 9% of the device) beats the UART link. P=16–32 is the sane first target, leaving DSPs free and keeping the adder trees easy to close timing on.

Input transport budget (2500 bytes + 1 byte result, 10 bit-times/byte):

| Baud | Frame time | End-to-end cap |
| --- | --- | --- |
| 115,200 | 217 ms | 5 inf/s |
| 921,600 | 27 ms | 37 inf/s |
| 1,000,000 | 25 ms | 40 inf/s |
| 3,000,000 | 8.3 ms | 120 inf/s |

Pick 1 Mbaud as the project target (works reliably over the FT2232H with pyserial 115200*8-style constant rates; verify loopback on day one).

## 3. Bottlenecks, ranked

- Your own time / debugging surface. Full-custom RTL CNN engines are where most hobby projects die. Mitigate with: layer-by-layer bit-exact verification against PyTorch, intermediate-activation dumps, and a v1 that has no convolution at all (see Phase 4).

- UART throughput (see above).

- BRAM (see above).

- Timing closure at 100 MHz for wide adder trees / big muxes. Mitigate with DSP internal accumulation, pipelining registers between stages, and P kept modest.

- Domain shift in accuracy — MNIST is 28x28; your 50x50 drawings are a different distribution. This is a data problem, not a hardware problem: build the drawing app early and collect your own samples in the exact preprocessing pipeline the hardware uses.

# PART 1 — What to learn

## Tier 1 — Neural networks, from the math up (~3 weeks)

You must be able to derive backprop by hand and implement conv/FC/ReLU/pool in NumPy without a framework. If you can't do it in NumPy, you can't design hardware for it.

- Michael Nielsen, Neural Networks and Deep Learning (free online) — backprop, gradient descent, MNIST. http://neuralnetworksanddeeplearning.com/

- d2l.ai, Dive into Deep Learning Ch. 3–7 (linear nets → MLPs → CNNs), with the PyTorch tab. https://d2l.ai/chapter_convolutional-neural-networks/

- Stanford CS231n course notes (free) — convolution as matrix multiply, im2col, receptive fields, pooling. https://cs231n.github.io/

- PyTorch 60-min blitz + torchvision — you need to train, save, and export weights confidently.

Output check: a PyTorch model that hits ≥99% MNIST, plus a NumPy reimplementation whose logits match the framework's to <1e-5.

## Tier 2 — DNN accelerator architecture (~4 weeks) — the most important tier

- Vivienne Sze, Yu-Hsin Chen, Tien-Ju Yang, Joel Emer, Efficient Processing of Deep Neural Networks (Morgan & Claypool / Springer, Synthesis Lectures on Computer Architecture). THE reference: dataflow taxonomy (weight-stationary / output-stationary / row-stationary), loop unrolling & tiling, PE arrays, memory hierarchy, energy-vs-throughput analysis. Free precursor paper: Efficient Processing of Deep Neural Networks: A Tutorial and Survey, arXiv:1703.09039 — read this first, then buy/borrow the book.

- MIT 6.5940 / 6.S965, TinyML and Efficient Deep Learning Computing (Song Han) — free lecture videos, slides, and 5 labs: pruning, quantization, neural architecture search, hardware accelerators. https://hanlab.mit.edu/courses — the "Hardware Acceleration" + "Quantization" lectures are directly on point.

- Stanford CS217, Hardware Accelerators for Machine Learning (Olukotun/Pedram) — lecture material on systolic arrays, dataflows, roofline.

- Papers worth reading properly (they are the vocabulary of this field):

  - Kung, "Why Systolic Architectures?" (1982) — the origin.

  - Chen et al., Eyeriss (ISCA 2016) — dataflow and energy per MAC.

  - Jouppi et al., TPU (ISCA 2017) — systolic array at scale.

  - Umuroglu et al., FINN (FPGA 2017) — binarized NN dataflow on FPGA.

  - Courbariaux et al. BinaryConnect; Rastegari et al. XNOR-Net; Zhou et al. DoReFa-Net — 1-bit weights/activations and how accuracy survives.

  - Sze et al. survey above, plus Guo et al., A Survey of FPGA-Based Neural Network Accelerators (arXiv:1712.08934) and Yan/Koch/Sinnen, A Survey on FPGA-based Accelerators for ML Models (arXiv:2412.15666, 2024 — the most current map of the field).

- Practical, blog-level: Adam Taylor's "MicroZed Chronicles" series on neural networks on FPGA (search "MicroZed Chronicles neural network"), and Xilinx WP486 Deep Learning with INT8 Optimization on Xilinx Devices for the vendor view of int8 on DSP48.

Output check: you can look at a network and, without a tool, say whether it fits in 225 KiB and how many cycles it takes at a given parallelism, and which dataflow you'd pick.

## Tier 3 — FPGA design for compute, not just logic (~4 weeks)

- Steve Kilts, Advanced FPGA Design: Architecture, Implementation, and Optimization — pipelining, resource sharing, area/speed tradeoffs, clock domain crossing, coding for synthesis. Exactly the book for "build a datapath", not "write a state machine".

- Uwe Meyer-Baese, Digital Signal Processing with Field Programmable Gate Arrays — MAC design, pipelining, systolic FIR structures, distributed arithmetic. The arithmetic architecture foundations; a convolution engine is a 2-D FIR filter wearing a hat.

- Pong P. Chu, FPGA Prototyping by Verilog Examples — reference designs for BRAM, FSMs, datapaths.

- Harris & Harris, Digital Design and Computer Architecture — if you want the textbook treatment of FP ALUs/FSM/datapath design to go with your existing RISC-V knowledge.

- Vendor docs you will actually open: UG479 (DSP48E1), UG473 (7-Series Memory Resources), UG901 (Synthesis), UG903 (Constraints), UG949 (Methodology), UG906 (Timing Analysis).

- ZipCPU tutorial + blog (zipcpu.com/tutorial) — FSM/datapath style, AXI handshaking, verification mindset.

- Cliff Cummings' papers (nonblocking assignments, coding guidelines) — the cheap way to avoid the classic simulation/synthesis mismatches.

Output check: a parameterized, pipelined MAC + a BRAM-based weight buffer + a clean FSM, each with a cocotb testbench, timing closed at 100 MHz, resource reports read and understood.

## Tier 4 — Quantisation & fixed-point numerics (~2 weeks) — where accuracy is won or lost

- Xilinx/AMD Brevitas (PyTorch quantisation-aware training, the front end of FINN) — docs + examples: https://github.com/Xilinx/brevitas

- QKeras / hls4ml docs for the "quantise then emit hardware" mindset: https://fastmachinelearning.org/hls4ml/

- PyTorch quantization recipe (PTQ + QAT) — https://docs.pytorch.org/tutorials/recipes/quantization.html and the classic Introduction to Quantization on PyTorch blog post.

- Key concepts to own: scale/zero-point, per-tensor vs per-channel scales, affine vs symmetric, power-of-two scales so requantisation is a shift instead of a multiplier, round-half-away-from-zero

  - saturation (must match your hardware exactly or accuracy silently degrades), accumulator width sizing (int8 x int8 x N needs log2(N)+16 bits), and the accuracy ladder: fp32 ~99.2%, int8 ~99.0%, 4-bit ~98.5%, 2-bit ~97%, 1-bit (BNN) ~95–97% with QAT.

Output check: same model, four precisions, accuracy table, and a bit-exact fixed-point simulator in NumPy.

## Tier 5 — Integration & verification (learning by doing, throughout)

- cocotb (you have it) for RTL testbenches driven by your NumPy golden model.

- UART framing / handshake protocol design + a Python host driver (pyserial) + a drawing GUI (Tkinter/PIL, pygame, or opencv-python for webcam).

- Vivado batch TCL builds (project already in your workflow).

- Optional: Vitis HLS (UG1399) — a legitimate second path where you write C++ and let the tool pipeline it. Useful for comparison and to understand what good scheduling looks like, but the learning (and the resume/portfolio value) is in writing the RTL.

## Do-NOT-waste-time list

- Float32 anywhere in the hardware. 90 DSPs cannot express fp32; fixed-point is the whole game.

- Vitis AI / DPU — DPUCZDX8G targets Zynq UltraScale+/Zynq-7000 with DDR; a pure-PL Artix-7 part is not a supported target. (Same for NVDLA — needs a big FPGA + DDR.)

- FINN on Artix-7 as your first path — FINN's supported flow assumes Zynq boards with PS+DMA; Artix-7 use is community-hacked (see Xilinx/finn discussion #508). Learn from FINN's ideas; build your own RTL.

- A 16x16 TPU-style systolic array as v1. You'd spend months on skew buffers and im2col before you ever see a digit classified. Earn it in Phase 5.

- Trying to beat a GPU/MCU on throughput. The point is building the machine, not winning a benchmark.

- Training on MNIST and assuming your own drawings will classify. Fix the data domain (Phase 6).

## Suggested reading order (10 weeks part-time)

- Wk 1–3: Nielsen + d2l Ch. 4–6 + CS231n notes → NumPy CNN from scratch.

- Wk 3–5: Sze survey paper → MIT 6.5940 quantisation + hardware lectures → Eyeriss + TPU papers.

- Wk 5–8: Kilts + Meyer-Baese (chapters on MAC/pipelining/systolic) + UG479/UG473 → pipelined MAC in RTL.

- Wk 8–10: Brevitas docs + PyTorch quantisation recipe + WP486 → quantise your model to int8 and prove the accuracy holds. Start Phase 0/1 of the build plan in parallel from week 3.

# PART 2 — End-to-end implementation plan

Repo layout (create it first; it survives every toolchain change):

npu-basys3/
├── training/       # PyTorch: model, train.py, quantise.py, export_weights.py
├── golden/         # NumPy bit-exact simulator (the contract the RTL must match)
├── rtl/
│   ├── compute/    # mac.v, mac_array.v, requant.v, relu.v, argmax.v, pool.v, conv_engine.v
│   ├── memory/     # weight_bram.v, img_buffer.v, line_buffer.v
│   ├── io/         # uart_rx.v, uart_tx.v, host_if.v (protocol FSM)
│   ├── npu_top.v   # accelerator core + control FSM
│   ├── top_basys3.v
│   └── hex/        # exported weight/bias hex files
├── sim/            # cocotb tests + testbenches
├── syn/            # basys3.xdc, build_basys3.tcl
├── host/           # python uart driver, drawing app, webcam demo
└── docs/           # per-phase results: utilisation, timing, accuracy, latency

## Phase 0 — Environment & loop (a weekend)

Goal: prove the whole toolchain before designing anything interesting.

- Vivado ML Standard (free; Artix-7 up to 100T supported), Digilent board files + master XDC (https://github.com/Digilent/digilent-xdc).

- Blink + UART loopback on the board: PC sends 8 bytes, FPGA echoes them. Establish the max baud you can run error-free for 10^7 bytes — this number sets your whole system's throughput.

- cocotb + Icarus/Verilator running one trivial test. Done when: bitstream programmed, loopback verified at your target baud (aim 1 Mbaud), and a cocotb test runs from the command line.

## Phase 1 — Software golden model + quantiser (1–2 weeks)

Goal: a model that fits the device and an export pipeline you trust.

- Decide architecture. Recommended: conv3x3(8) → ReLU → maxpool2 → conv3x3(16) → ReLU → maxpool2 → FC(10) on 50x50 → 20 KiB weights, 863K MACs. Optional MLP fallback at 28x28 (784-64-32-10) if you want a trivial first target.

- Train in PyTorch on MNIST upscaled to 50x50 (and/or Google Quick, Draw! 28x28 bitmaps, https://github.com/googlecreativelab/quickdraw-dataset — 50M drawings, free, npy/28x28).

- Quantise: int8 weights, uint8 activations, int32 accumulators, per-tensor power-of-two scales. Export weights.hex/biases.hex ($readmemh-compatible), plus a JSON manifest of every scale. Done when: quantised accuracy is within ~0.5% of fp32 and weights fit in ≤10 BRAM blocks (documented in docs/).

## Phase 2 — Bit-exact NumPy "hardware model" (1 week)

Goal: the specification the RTL is verified against — not a floating-point model.

- Implement the exact integer dataflow in NumPy: fixed widths, fixed rounding (round-half-away-from-zero), saturation, shift-based requantisation, shift-add only where the hardware will.

- Generate frozen test vectors: input image bytes → per-layer activation dumps → logits → argmax. Done when: golden/vectors/ contains N test cases with per-layer intermediates, and the quantised accuracy claim is reproduced by this integer model. This step is what makes the RTL debuggable.

## Phase 3 — RTL building blocks, bottom-up with cocotb (2–4 weeks)

Order (each one gets a testbench that compares against the golden model, bit-exactly):

- mac.v — signed int8 x int8, int32 accumulate, valid/clear, 1–3 pipe stages. Check DSP inference in the synthesis log (report_utilization → DSP48E1 count) instead of trusting the tool.

- mac_array.v — P parallel MACs + adder tree (P=16 first), registered inputs and outputs.

- requant.v — shift, round, saturate to the next layer's activation width. Test with the nasty values: max/min int32, exact .5 ties, saturation edges.

- weight_bram.v — weights in BRAM, one row per cycle, plus a $readmemh init path. Watch the classic trap: a wrong $readmemh path silently yields an all-zero ROM. Grep the synthesis log for $readmem data file ... is read successfully on every build.

- relu.v, argmax.v (first-index-wins on ties, matching NumPy), pool.v.

- fsm — layer sequencer: address generation, valid gating (accumulating garbage is the #1 silent bug), done/busy handshake. Milestone: a layer-level testbench that runs layer 1 of the network end-to-end and matches the golden activation dump byte-for-byte.

## Phase 4 — v1 accelerator: MLP on the board, end-to-end (3–5 weeks)

Goal: a hand-drawn digit classified on real hardware. Do not attempt convolution yet. Reduce input to 28x28 (784 bytes) if it shortens this phase; the point is the full loop.

- npu_top.v: weight BRAMs + MAC array + layer FSM + argmax, MMIO-style registers (control, status, result, write-data, write-addr).

- host_if.v: UART framer — 0xA5 | len | payload | checksum, DMA-ish pixel streaming into img_buffer.

- Integration choice: either bare RTL host-IF FSM (simplest, recommended), or reuse your R32 RISC-V core as the control processor with the NPU as an MMIO peripheral at e.g. 0x4000_0000 — you already have that pattern working on this board, and it makes the demo firmware trivial.

- Outputs: prediction on LEDs (LD3:0) and the 7-seg display; raw logits over UART for debugging.

- Host: host/draw_gui.py — draw with the mouse, downsample to the model resolution, send, display result. Done when: (a) sim matches golden for all vectors, and (b) on board, 20/20 digits you draw are classified with the same result the host-side integer model predicts. Log per-stage latency and utilisation in docs/.

## Phase 5 — CNN engine at 50x50 (6–10 weeks) — the actual NPU

- Line buffers: 3-row circular line buffer so one new pixel per cycle feeds a 3x3 window (no im2col materialisation in memory). Read Kilts on pipelining and Meyer-Baese on 2-D FIR structures first.

- Weight-stationary conv engine: Cout filters mapped across PEs, weights loaded once per layer, activations streamed; the 9 taps of the 3x3 window are the natural P=9 inner dimension. See sharatchandra-ts/systolic-TPU-CNN-accelerator for a 9x4 SystolicConv/SystolicFC split (SystemVerilog).

- Pooling as a streaming 2x2 max on the way out of the conv stage; FC layer as an output-stationary tile loop.

- Optional DSP48E1 tricks: use the internal 48-bit accumulator (MACC) instead of an external adder tree, and the pre-adder to fold two window terms before the multiply — both cut LUT pressure significantly.

- 2x clocking: put the compute array on a 200 MHz MMCM output if it closes (DSP48E1 goes far higher than the fabric); revisit only if you're throughput-starved. Done when: 50x50 CNN classifies on board at the target baud, accuracy matches the integer golden model within rounding, and timing is closed (positive WNS) at the chosen clock.

## Phase 6 — Demo & data domain (2 weeks)

- Drawing app (Tkinter/PIL): 50x50 canvas, mouse strokes, same normalisation/downsampling as training, live prediction, "save sample + label" button. Collect ~500 of your own drawings.

- Retrain on MNIST-upscaled + QuickDraw + your own samples; re-quantise; re-export. This is where the accuracy for your drawings comes from.

- Display upgrade (optional, high demo value): 12-bit VGA out showing the 50x50 image beside the prediction — Basys3 has VGA, and it makes the project obviously real.

- Webcam path (like adithyarg/MLP-Accelerator-for-MNIST-on-Basys3-FPGA does) if you want hands-free demo.

## Phase 7 — Stretch goals

- Per-channel scales + mixed precision (4-bit weights, 8-bit activations) for a bigger model.

- Store a test set in the 4 MB QSPI flash (10,000 MNIST images = 7.84 MB, so ~5,000 fit) to benchmark THROUGHPUT without the UART in the loop.

- BNN variant (1-bit weights, XNOR + popcount in LUTs instead of DSPs) — a genuinely different datapath and a great comparison table for your write-up.

- Compare against hls4ml on the same network — a defensible "hand-written RTL vs HLS" analysis.

- Port to Arty A7-100T (2.7x BRAM, 240 DSP) — same RTL, one line of TCL changes.

## Reference designs to read (in this order)

| Project | Why it matters |
| --- | --- |
| adithyarg/MLP-Accelerator-for-MNIST-on-Basys3-FPGA | Closest match to your target. Basys3, XC7A35T, 784-64-32-10 MLP, Q4.12/Q8.8 fixed point, UART at 115200, webcam host, 94% MNIST, ~2.1 ms, Vivado 2024.2 + full TCL build, host protocol documented. Read the report.md and training/quantize.py first. |
| haydenthai/FPGA-Neural-Network-Inferencer | Same board but with PicoRV32 as host + MMIO accelerator + 7-seg + flash boot. The template for the soft-core-host architecture (near-identical to what your R32 core can do). |
| sharatchandra-ts/systolic-TPU-CNN-accelerator | SystemVerilog CNN: weight-stationary 9x4 systolic conv array, im2col address generator, skew unit, output-stationary FC with tiling, MaxPool, Argmax. The Phase 5 template. |
| Xilinx/finn + Xilinx/brevitas docs | Vocabulary of QNN dataflow, plus a QAT library you can actually use for Phase 1 even if you hand-write the RTL. |
| fastmachinelearning/hls4ml | Quantise→emit-hardware reference and a comparison baseline. |
| Google Quick, Draw! dataset | Free 28x28 line-drawing data at 50M scale — the antidote to MNIST domain shift. |

## Pitfalls that will cost you days

- $readmemh paths are CWD-relative and a bad path is silent (all-zero ROM). Grep the synthesis log for read successfully on every build; pass an absolute path via a parameter.

- Accumulating on invalid beats: gate accumulation with valid or you get plausible-but-wrong numbers.

- Rounding mismatch between Python and Verilog (banker's vs half-away-from-zero, floor vs truncate on negatives). Fix it in Phase 2 with nasty test vectors or you will chase a "quantisation accuracy drop" that is actually a rounding bug.

- Adder-tree width: int8 x int8 x 9 taps needs 16+4 = 20+ bits before saturation; size the accumulator from the worst case, not the average.

- xsim rejects forward-declared identifiers that Icarus and Vivado synthesis accept — simulate with Icarus/Verilator (you already do).

- Uninitialised FSM/divider registers simulate as x in Icarus and freeze downstream logic; give them explicit initial values.

- Timing: read the routed report_timing_summary (WNS/WHS) every iteration. If 100 MHz fails, find the critical path before reducing the clock — usually it's a wide mux or an unregistered BRAM output.

- Only one process can hold a COM port — a stale Python host leaves "Access is denied" and looks like broken hardware.

- Don't build the CNN first. v1 = MLP, on the board, classifying digits. Everything after that is optimization with a working reference in hand.

## Realistic schedule (part-time, your current skill level)

| Phase | Duration | Cumulative |
| --- | --- | --- |
| Learning tiers 1–4 (in parallel with Phase 0–1) | 8–10 weeks | 10 wk |
| 0 Environment/loop | 1 wk | 1 wk |
| 1 Golden model + quantiser | 2 wk | 3 wk |
| 2 Integer simulator | 1 wk | 4 wk |
| 3 RTL blocks + cocotb | 3 wk | 7 wk |
| 4 MLP accelerator on board (v1 demo) | 4 wk | 11 wk |
| 5 CNN engine at 50x50 | 8 wk | 19 wk |
| 6 Demo, own-data retrain, VGA | 2 wk | 21 wk |

~5 months part-time to a CNN NPU on a Basys3 classifying your own hand-drawn digits at ~40 inf/s (link-limited). A respectable, publishable/write-up-able project — and everything transfers to Arty A7-100T, Zynq, or (via the same RTL discipline) an ASIC flow.